## Slide 1: How to Approach the Fit-to-Standard Analysis in the Cloud
August, 2022

## Slide 2: Purpose of This Document SAP Activate Methodology Accelerator
The purpose of this accelerator is to enable and educate users on the fit-to-standard process to ensure a successful fit-to-standard that captures all configuration and integrations needed for the solution- creating an efficient and effective solution configuration in Realize.
Project Lead
Business Process Expert(s)
Configuration Expert(s)
Document Target Audience:
Please Note: Detailed information on the Integration Process is not covered in this presentation. For detailed information regarding the integration process, for Integration Implementation Experts, please refer to the integration accelerator.

## Slide 3: Fit-to-Standard Process Purpose
    Enabling customers on the business processes included in the solution scope
    Validating that the scope and business processes meet the business needs
    Determining core configuration values based on business drivers
    Identifying configuration values lists to be provided by the business
    Defining organizational structure and chart of accounts
    Defining required master data
    Defining authorization mapping
    The purpose of the Fit-to-Standard Process is to match the customer’s business processes to the standard processes available and to capture optimization, solution configuration, needed by the customer. It is a sub-process in the Application: Design and Configuration workstream.
Purpose is Met By:

## Slide 4: Content
Overview and High Level Steps
Process Inputs
Process Execution
Process Outputs
Sample Schedule
General Principals

## Slide 5: Fit-to-Standard Process Overview: Inputs and Outputs
Fit-to-Standard Process
Scoping Process
Optimization Process
Solution Configuration Process
Discover
Prepare
Explore
Realize
Implementation Phase Occurs:
Solution Realization
Configuration Assessment
Customer Enablement
Fit-to-Standard Preparation
Discovery Assessment
Process Inputs:
Process Outputs:
Fit-to-Standard Documentation
Customer Enablement
Planning and Design
Scope Statement

## Slide 6
Fit-to-Standard Documentation
Solution Realization
Fit-to-Standard Workshops
Prepare
Explore
Fit-to-Standard Workshop Preparation
Discovery Assessment
Configuration Assessment
Realize
Implement Backlog
Sprints and Confirmation with Business and IT
1-2 wks
1-2 wks
Customer Self-Enablement
Discover
Customer Execution of Standard Scenarios
Scoping Process
Optimization Process
Solution Configuration Process
Release Planning
Fit-to-Standard Process High Level Steps
Planning and Design Workshops
Integration
Extensibility
Project Lead
Business Process Expert(s)
Configuration Expert(s)
Technical Expert(s)
Service Center
Key Roles:
Fit-to-Standard System Preparation
Execute Workshop – Identify Backlog Items and Requirements
Process Flows /Test Scripts
Show and Tell
Configuration Questions
Customer Feedback
Document Workshop Findings
Build Backlog
Key Business Decisions
Roadmap items
Confirmation of scope
Process Models
Delta Requirements
Analytics
Master Data
User Access and Security
Create Project Charter and Scope Statement

## Slide 7: Fit-to-Standard - Process Inputs
Prepare
Discover
Project Lead
Business Process Expert(s)
Configuration Expert(s)
Technical Expert(s)
Key Roles:
Fit-to-Standard Workshop Preparation
Configuration Assessment
Fit-to-Standard System Preparation
Customer Self-Enablement
The Business Process Expert verifies access to Implementation tools and begins solution enablement
Scoping process to capture all scope items and integration requirements needed.
Configuration Expert sets scope based on project initial scope and sent to Business Process Experts. Business Process Experts provide written feedback to business questions and return completed questionnaire(s).
The Business Process Expert verifies access to the Fit-to-Standard System and enables themselves on all accelerators used during the Fit-to-Standard process. In addition, all requirements captured in the Discover Phase are transferred to the initial list.
The Fit-to-Standard System is prepared for the Fit-to-Standard workshops by reviewing Master Data pre-delivered and additional sample data is created if needed.
Business Driven Configuration
Customer Enablement
Fit-to-Standard Preparation
Discovery Assessment
Scope Statement
Discovery Assessment
Create Project Charter and Scope Statement
The scope statement is created based off of scoping discussions and determination in Discover

## Slide 8: Fit-to-Standard Process
Explore
Fit-to-Standard Process
Fit-to-Standard Documentation
Customer Enablement
Planning and Design
Project Lead
Business Process Expert(s)
Configuration Expert(s)
Technical Expert(s)
Service Center
Key Roles:
Fit-to-Standard Documentation
Fit-to-Standard Workshops
Customer Execution of Standard Scenarios
Release Planning
Planning and Design Workshops
Integration
Extensibility
Execute Workshop – Identify Backlog Items and Requirements
Process Flows /Standard Scripts
Show and Tell
Business Driven Configuration Questions
Customer Feedback
Document Workshop Findings
Build Backlog
Key Business Decisions
Roadmap items
Confirmation of scope
Process Models
Delta Requirements
Analytics
Master Data
User Access and Security
Business Driven Configuration Questionnaires are used as a reference during the Fit-to-Standard workshops. Answers are used to foster discussion to help identify backlog items and requirements needed for the solution realization. All backlog items and delta requirements are defined and documented in each workshop. There can be multiple waves for each Fit-to-Standard workshops depending on the topics.
All process flows, backlog items, and delta requirements are reviewed and validated for completeness after being defined during the Fit-to-Standard Workshops.
All backlog items are reviewed and consolidated into one Backlog. The scope for the first implementation phase is determined and items descoped are documented for future implementation phases
Handover of requirements and process flows to expert teams and delta requirements are reviewed and converted into backlog items.
Business Process Experts execute scenarios demonstrated during the Fit-to-Standard workshops in the Starter System.

## Slide 9: Fit-to-Standard Process Overall Workshop Execution Approach
1
2
4
5
Review Best Practices process flow
Demonstrate
Scope Item
and
Concepts
Discuss how the processes fit with the customer’s
requirements
Identify required configuration
Enable customer execution of standard scenarios
Configuration expert enables the business process expert to execute the process on their own in the Starter system.
Team leverages the Business Driven Configuration Questionnaire to arrive at critical configuration decisions. All configuration values required and any needed in-app extensions are determined and documented in the backlog. The customer is responsible for providing value lists. i.e. product group definition.
Configuration expert demonstrates the scope item using the starter system and delivered master data and highlights the areas that require configuration decisions. The process flow is used as a point of reference when transitioning in the system.
Configuration expert explains the scope item using the SAP Best Practices process flow and responses from the Business Driven Configuration Questionnaire.
Team fosters discussion to better understand the customer business requirements, referencing the Business Driven Configuration Questionnaire, and to provide understanding of how the solution meets these requirements.
Identify Delta Requirements
Team identifies and catalogs the delta requirements in the backlog for further analysis and closure. Delta requirements are business requirements that cannot be satisfied with the standard scenarios.
6
3
* Repeat process for each scenario
**Iterate through all process variations
Business Process Expert(s)
Configuration Expert(s)
Backlog
Delta Requirements

## Slide 10: Fit-to-Standard Process Decision Tree
*For additional information on extensions see SAP Activate Methodology for Developing Cloud Extensions methodology roadmap
*

## Slide 11: Fit-to-Standard Process Outputs of the Workshops
    Solution impact on business processes
    Delta requirements identification and mitigation
    SAP Best Practices enablement
    Configuration values required
    Value-add impact for users and business
    Expert configuration definitions
    Awareness of KPIs addressed and impacted
    Forms, reports, and authorizations requirements
Business Driven Configuration Questionnaire (Final)
Backlog (Prioritized)
Meeting Minutes & Action items (Reviewed & Finalized)
Sign off of Key Decisions
OUTPUTS
Updated Integration and Interface List
Business Process Expert(s)
Configuration Expert(s)
Updated Process Flows
Configuration Expert(s)
Configuration Expert(s)
Business Process Expert(s)
Configuration Expert(s)
Business Process Expert(s)
Business Process Expert(s)
Configuration Expert(s)

## Slide 12: Fit-to-Standard Process Outputs
Solution Realization
Realize
Configure and setup the system using the consolidated Backlog.
    The purpose of the Solution Realization process is to optimize the solution, for the first implementation phase, in sprints based on the consolidated backlog from the Fit-to-Standard and Planning and Design processes.
Solution Realization
Implement Backlog
Sprints and Confirmation with Business and IT
1-2 wks
1-2 wks
Project Lead
Business Process Expert(s)
Configuration Expert(s)
Technical Expert(s)
Key Roles:
Service Center

## Slide 13: Fit-to-Standard Workshop Schedule (Example)
Scope validation | Duration (days) | Week 1 |  |  |  |  |  | Week 2 |  |  |  | 
 |  | M | T | W | TH | F |  | M | T | W | TH | F
Conduct Fit-to-Standard for Chart of Accounts | 1 |  |  |  |  |  |  |  |  |  |  | 
Conduct Fit-to-Standard for Organizational Structure | 1 |  |  |  |  |  |  |  |  |  |  | 
Conduct Fit-to-Standard for Human Resources | 2 |  |  |  |  |  |  |  |  |  |  | 
Conduct Fit-to-Standard for Sales | 3 |  |  |  |  |  |  |  |  |  |  | 
Conduct Fit-to-Standard for Sourcing and Procurement | 2 |  |  |  |  |  |  |  |  |  |  | 
Conduct Fit-to-Standard for Manufacturing | 3 |  |  |  |  |  |  |  |  |  |  | 
Conduct Fit-to-Standard for Project Services | 2 |  |  |  |  |  |  |  |  |  |  | 
Conduct Fit-to-Standard for R&D Engineering | 1 |  |  |  |  |  |  |  |  |  |  | 
Conduct Fit-to-Standard for Supply Chain | 2 |  |  |  |  |  |  |  |  |  |  | 
Conduct Fit-to-Standard for Asset Management | 1 |  |  |  |  |  |  |  |  |  |  | 
Conduct Fit-to-Standard for Finance | 3 |  |  |  |  |  |  |  |  |  |  | 
Conduct Fit-to-Standard for Service | 1 |  |  |  |  |  |  |  |  |  |  | 
Please Note: The Fit-to-Standard Workshops, shown above, can take place in parallel and they can take place in any sequence. As a best practice we suggest the Conduct Fit-to-Standard for Chart of Accounts and Organization Structure take place first and second and the Conduct Fit-to-Standard Workshop for Finance take place last.

## Slide 14: Individual Workshop Schedule and Planning and Scope (Example)
Workshop Focus | Workshop Scope | Scope items to be covered | In Scope (I)/ Out of Scope (O) | Participants (Key Users)
Contract to Cash | Contract to Cash |  |  | 
 | Contract to Cash | J11 1IL 16T J14 1P0 | I I O O O | Project manager commercial services, Purchaser, Internal Sales representatives, Billing clerk, General Ledger Accountant, Controller
Time and Expense Management | Time and Expense Management |  |  | 
 | Time and Expense Management | 1M1 J11 J12 | O I I | Project Manager Internal Services, Purchaser, General Ledger Accountant, Controller, Internal Sales Representative, Billing Clerk
Project Management | Project Management |  |  | 
 | Project Management | 1KC 2MV BGI J11 1IL 1A8 J13 BGJ 1P0 | I I O I I I O O O | Project Manager Internal Services, Purchaser, General Ledger Accountant, Controller, Internal Sales Representative, Billing Clerk
Scope Validation | Duration (days) | Week 1 |  |  |  | 
Professional Services |  | M | T | W | Th | F
Contract to Cash | 1 |  |  |  |  | 
Time and Expense Management | 1 |  |  |  |  | 
Project Management | 1 |  |  |  |  | 
Professional Services
Conduct Workshop

## Slide 15: General Fit-to-Standard Workshops Principals
Workshop Best Practices should still be followed:
Plan in detail with templates for workshop inputs and outputs.
Set boundaries and understand expectations at the start of each workshop.
Provide process, value and strategic context at start of each workshop.
Focus on business value and tie to business case and value drivers.
Access the Scope Item Process Diagram, Process Model and Test Scripts within the SAP Best Practices Explorer in the Scope Item details to explain and demo the S/4HANA solution functionality.
Build off Business Driven Configuration Questionnaire(s) filled out by the customer to clarify and make critical configuration decisions.
Discuss any scope that has/may be impacted by a system upgrade – refer to “What’s New” Help documentation for further guidance.
Prioritize scope and configuration.
Document decisions, assumptions and business impacts of new processes.
Produce detailed documentation immediately and align with customer.
Formal sign-off of key decisions and required configuration before realize phase starts.
Time is limited, scope validation is not a training session, time box to drive decision making.
Table parking lot items.

## Slide 16: Thank you.
SAP Activate Methodology